## Gantt Chart
Production Schedule
PROJECT TITLE |  | The Greatest Sandwich Ever Sold |  |  |  |  | COMPANY NAME | [6 empty] | Robot Destroyers from Outer Space
PROJECT MANAGER |  | Rick Larsen |  |  |  |  | DATE | [6 empty] | 2018-09-22
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Write crowdfund proposal | Rick L | 2018-10-01 | 2018-10-05 | 4 | 15% | bar: WEEK 1 M to WEEK 1 F
1.1.1 | Identify Crowdfund site | Tommy C | 2018-10-03 | 2018-10-05 | 2 | 0% | bar: WEEK 1 W to WEEK 1 F
1.2 | Design donor rewards | Tommy C | 2018-10-08 | 2018-10-13 | 5 | 25%
1.3 | Launch campaign | Rick L | 2018-10-12 | 2018-10-12 | 0 | 0% | bar: WEEK 2 F
1.4 | Monitoring | Rick L | 2018-10-12 | 2018-11-12 | 30 | 0% | bar: WEEK 3 M to WEEK 7 M
2 | Project Definition and Planning
2.1 | Confirm filming location | Tommy C | 2018-10-12 | 2018-10-12 | 0 | 100% | bar: WEEK 2 F
2.2 | Design sets | Dain G | 2018-10-29 | 2018-11-09 | 10 | 0% | bar: WEEK 6 M to WEEK 7 F
2.3 | Design props | Dain G | 2018-10-29 | 2018-11-09 | 10 | 0% | bar: WEEK 6 M to WEEK 7 F
2.4 | Design costumes | Dain G | 2018-10-29 | 2018-11-09 | 10 | 0% | bar: WEEK 6 M to WEEK 7 F
2.5 | Rehearsal / script revision | Arturo R | 2018-11-05 | 2018-11-10 | 5 | 0% | bar: WEEK 7 M to WEEK 7 F
3 | Project Conception and Initiation
3.1 | Art approvals | Rick L | 2018-11-09 | 2018-11-09 | 0 | 0% | bar: WEEK 7 F
3.2 | Final Rehearsal | Arturo R | 2018-11-10 | 2018-11-10 | 0 | 0%
3.2.1 | Venue Set up | Dain G | 2018-11-10 | 2018-11-11 | 1 | 0%
3.2.2 | Principal filming | Rick L | 2018-11-11 | 2018-11-12 | 1 | 0%
3.3 | Initial editing | Bill B | 2018-11-12 | 2018-11-19 | 7 | 0%
3.3.1 | Reshooting | Rick L | 2018-11-21 | 2018-11-22 | 1 | 0%
3.3.2 | Final editing | Bill B | 2018-11-22 | 2018-11-30 | 8 | 0% | bar: WEEK 9 M to WEEK 9 F
4 | Project Performance / Monitoring
4.1 | Preview screening for Donors | Tommy C | 2018-12-07 | 2018-12-07 | 0 | 0% | bar: WEEK 10 F
4.2 | Distribute donor rewards | Tommy C | 2018-12-01 | 2018-12-07 | 6 | 0% | bar: WEEK 10 M to WEEK 10 F
4.3 | Festival submissions | Rick L | 2019-01-01 | 2019-06-30 | 179 | 0% | bar: WEEK 11 M to WEEK 12 F
4.4 | Video release (online) | Rick L | 2019-07-04 | 2019-07-04 | 0 | 0%